## tasks processes 160408 deutsch
No. | Task | Description | Responsible | Team | finish date | Result/ further action | Information Status (Open/Closed)
Kölbl & Lehmann Col., Ltd
1 | Rene | Resignation as Director | Lutz | Tammy Lutz | 2011-06-30
2 | Payment Calendar | Whom do we want to pay | Rene | Tammy Lutz | 2011-06-30
3 | Assets | List of assets, what can we transfer to the bank and what not | Rene | Tammy Lutz | 2011-06-30
4 | Small assets | Wo to do with all the furniture, computer, ac etc… | Rene | Tammy Lutz | 2011-06-30
5 | Termination | Ludwig & Thomas termination to be arranged | Rene | Tammy Lutz | 2011-06-30
| Houses | We also have to terminate all cars and housing we do not need anymore | Rene | Tammy Lutz | 2011-07-15
6 | Winding up Kandl | we have to close Kölble & Lehmann and Sura has to help us for the next steps | Rene | Tammy Lutz | 2011-06-30 |  | We have to include Sura
7 | Moving out all out of the office and production | Moving plan and sotrage plan to be arranged | Tammy | Rene Lutz | 2011-08-31
8 | Production processes | We have to start writiung down all production processes | Albert | Rene Lutz | 2011-08-31
| Office processes | We have to start writiung down all production processes | Tammy | Lutz | 2011-07-15
9 | Review calculation | The complete calculation has to be reviewed and set up | Albert | Rene Lutz | 2011-08-31
10 | Customer base | We have to set us the new customer base and the goals we want to achieve | Rene | Albert Lutz | 2011-08-31
11 | Supplier / customer contracts | analyse and review all the contract situation | Lutz | Tammy Rene | 2011-08-31
12 | Salesfolder for sales people and marketing | Prepare a good folder for advanced sales | Lutz | Lutz Rene Mam | 2011-08-31
13 | Budget Planning for machinery park | Thinking about new investments,terms of depriciation, etc.. | Lutz | Bernd Rene tammy | 2011-06-30
14 | Phuket | We have to decide what to do with the Phuket location | Rene | Tammy Lutz | 2011-07-15
Bavarian Sausages Co., Ltd
1 | Signatures | I have to signed all relevant documents | Lutz | Tammy | 2011-07-04 |  | Where???????
| Authority Signature | We have to arrange authority signature for Rene and me | Tammy | Lutz | 2011-07-04
2 | Generate OD / FTY Credit | Talk to the bank toget the OD and credit for the fty for the new company | Lutz | Tammy Rene | 2011-07-04
3 | Factory | We have to decide on the factory location and buying process | Lutz | Tammy Rene | asap
4 | Fty planning | We have to arrange te outlook and floorplan of the fty when bought | Rene | Albert Lutz | after buying
5 | Employment Contracts | We have to arrange all new emplyoments contracts | Tammy | Lutz | 2011-08-31
6 | Design Patent | Register the logo | Tammy | Lutz | 2011-07-04
7 | Internet Presentation | We have to redsign the inernet Presence | Lutz | Tammy Rene | 2011-08-31
8
9
10
11
<root/>

## tasks processes 160408 english
Bavarian Saussage Co., Ltd
Action list for various projects
Attendences:
2011-03-05
Nr. | TASK | Sub Task | Responsible | Team members | Target achievement date | Result/further proceeding | Informationen / Status(Open/Closed)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Umstellung der Prozesse, action list
1
2
3
4 | [6 empty] | closed
5
6 | [6 empty] | closed
7
8
9
10
11